## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product
B | Develop marketing strategy
C | Design brochure | A
D | Develop product prototype
D1 | Requirements analysis | A
D2 | Software design | D1
D3 | System design | D1
D4 | Coding | D2, D3
D5 | Write documentation | D4
D6 | Unit testing | D4
D7 | System testing | D6
D8 | Package deliverables | D5, D7
E | Survey potential market | B, C
F | Develop pricing plan | D8, E
G | Develop implementation plan | A, D8
H | Write client proposal | F, G